Model Health and Safety Plan

This record is provided by the Health and Safety Department and Aon Risk Services, the University's insurance brokers, as a template, which provides a basic outline for a health and safety plan. A health and safety plan is recommended as a way of formally identifying the health and safety issues in each management unit and setting out a timetable for these issues to be addressed.

Formal plans help to demonstrate to outside observers such as Auditors, Health and Safety Executive Inspectors, etc that efficient health and safety managerial systems are in place.

The model plan will require to be amended and/or expanded to address fully the ongoing issues relevant to each area, and therefore should not be regarded as exhaustive.

| ## Subject / Item | ## Person Responsible | ## Target Date | ## Status |
| --- | --- | --- | --- |
| Health & Safety Committee meetings (once per term) | WP | January May September | Completed 15/01/2010 - minutes distributed |
| Office safety review, incl workstation assessments and manual handling assessments | AB | March 2010 | Programme planned |
| Review all COSHH assessments | DJ | April 2010 |  |
| Health and Safety awareness training for managers and Area Safety Adviser | WP | May 2010 | Contact Health and Safety Department for available dates |
| Fire Awareness Training | JW | June 2010 | Coordinate with Health and Safety Department |
| New lab risk assessments (COSHH, General, GM, etc) | DS | July 2010 |  |
| Review biological containment laboratory protocols | AB | July 2010 |  |
| Laboratory fume cupboard performance checks | DS / Works Division | Aug 2010 | Remind WD of new fume cupboards; ensure all tests completed by required date |
| PAT testing review |  |  | Add new items to register; delete obsolete items, ensure testing up-to-date |
| School safety audit | AB/PC/DJ | Oct 2010 |  |
| Servicing of specialist lab equipment (on contract) | DS | Oct 2010 |  |
| Engineering tests of lifting equipment (Contractor via WD) | AB/DJ | Nov 2010 | Notify WD of new equipment; ensure all tests completed by required date |
| Policy review | AB | Dec 2010 |  |
| Safety plan review | AB/RE | Dec 2010 |  |